## Risk Assessment 2024
|  | IDENTIFIED RISK | ACTION TAKEN/REQUIRED | 2024 UPDATE
Council Owned Property
1. | Roof of Civic Hall | Hall unusable, claims for loss of income | Reroofing approved by Council Feb 16. | -
2. | Accidents at Civic Hall | Claims, litigation | Inspection, insurance. | -
3. | Civic Group struggle or collapse | Loss of income | Maintain strong, firm relationship | New lease being arranged for 3 years.
|  | Empty building - vandalism etc. | Secure the building until re-let
4. | Rear of Civic Hall | Failure to let - vandalism, loss of income |  | Unit let.
5. | Incubator unit offices | Local economy weakens so income falls | Pay for more car park spaces if needed | Continue to monitor. All offices are let.
Problem tenants (not yet arisen)
Car parking disputes
6. | Lease with WCC not yet signed | WCC increase service charge | Chase solicitors to finalise lease | Under discussion. Contact has now been made and progressing.
WCC create difficulties in relation to tenancy
7. | Civic Centre furniture and office equipment | Fire | Computer data save | Contingency Plan in progress.
|  | Data Loss | Repair and Renewal Fund
Insurance
Appliance Testing
Maintenance Contract/Self Insurance
Security Software
Contingency Planning
Annual Health and Safety inspection
8. | Stourport Community Centre | Loss of income | Maintain strong, firm relationship | Managed by Town Council. Promotion of centre is through Facebook and website.
Empty building - vandalism etc.
9. | Elizabeth Mills Centre | Empty building - vandalism etc. | Maintain strong, firm relationship | Taken over in December 2023. Lease continues until 2026.
Town Council staff, administration and governance
10. | Staff | Loss of key staff especially if at same time | Periods of notice | New staff have contracts
Business continuity plans
11. | Governance and business procedures minimal | Exposure to financial loss and claims | Secure Council approval of procedures | -
12. | Responsibility for Health and Safety | Accidents to staff and/or service users, exposure to claims and financial loss and reputational damage | Health and Safety Contract taken out with WorkNest (formerly Ellis Whittam.) Annual Inspections | Town Clerk in contact with Health and Safety Company.
13. | Land and property registration and database | Claims, disputes, admin costs etc. | Establish registration and database. Town Clerk working with WFDC. | Actively being progressed.
14. | Elected members | Insufficient future quantity and/or quality | Initiatives to encourage public interest. Council elections in May 2023. | Website and Facebook page constantly updated when required.
Town Council Finances
15. | Unexpected costs or sudden fall in income | Unplanned cuts to services during financial year | The Council budgets carefully each year and maintains a minimum balance of £70,000 and other funds for specific purposes. | Budget report draws members attention to the issue.
Abberley Avenue
16. | Public Open Space (Common Land) | Management and Maintenance | Grass cutting in growing season | -
Areley Kings
17. | Recreation Ground | Management and maintenance | Insurance | -
Annual Health and Safety inspection
Bollard installed for extra security
Extra benches and bins installed
Taken over MUGA from WFDC
Trees Planted
Allotment Land
18. | Kingsway | Management and maintenance of sites. Damage to site, loss of income, non-compiance with rules etc. | Allotment Rep at each location. Insurance. Attendance by Parks Manager at allotment committee meetings. | New Management Committee set up.
19. | Areley Kings |  |  | -
Cemetery, Minster Road
20. | Land | Vandalism, Management and Maintenance | Annual Health and Safety inspection, on site staffing, frequent inspections by Cemetery Supt. | -
21. | Cemetery Portakabin | Damage, Fire and Safety of staff and visitors | Insurance. | -
Hazardous substances stored at Memorial Park.
22. | Cemetery Toilet Block | Damage, Fire and Safety of staff and visitors | Appliance Testing | -
23. | Cemetery Office Contents | Damage, Fire, theft and Medical Pandemic | Contingency Planning | -
Computerising of cemetery records ongoing.
Vale Road / Lion Hill
24. | Public Gardens and War Memorials | Management, Maintenance and Vandalism | Insurance | -
|  | Weather Damage | Arboricultural survey
|  | Safety of general public | Daily visits and visual checks by Staff
Memorial Park
25. | Stourport Com Centre - Changing Rooms, Building | Damage, Fire and Safety of staff and visitors | Arboricultural 2 year remedial work | -
26. | Stourport Com Centre - Changing Rooms, Contents | Damage Fire and theft | Grass cutting in growing season | -
27. | Memorial Park Bandstand | Materials Damage | Daily visit by staff | Bandstand railings repairs in 2023.
New benches and bins installed
Tree Planting
28. | War Memorial Gates, Railings and Play Equipment | Damage and theft | Contingency Planning | -
Annual Health and Safety inspection
Green Gym, Play Areas
29. | Trees within Memorial Park and other sites | Damage and falls, Safety of general public. | Tree inspection and Management SLA with Wyre Forest District Council | Agreement in place. Ongoing works scheduled.
Open Spaces
30. | Foundry Street | Management and Maintenance and Vandalism | Insurance | -
31. | Lloyds Meadow
Riverside
32. | Paddling Pool | Vandalism and Damage | Insurance | Continue with improvements and monitoring
|  | Flooding from River | Annual cleaning and maintenance programme
|  | Hazardous Chemicals | Pump house securely padlocked
|  | Safety of general public | Contractors employed for daily water and safety checks (during operation of pool)
Regular view of Risk Assessment and meetings
Gates securely padlocked when not in use
Town Clock and Clock Tower
33. | Town Clock and Tower | Management and Maintenance | Weekly inspection | Ongoing
Insurance
Structural Engineer Inspections
Bus Shelters and Public Seats
34. | Bus Shelters and Public Seats | Management and Maintenance | Insurance | -
|  | Vandalism | Inspection
Staff patrols
Street Lighting
35. | Street Lighting | Management and Maintenance | Insurance | -
|  | Vandalism | Inspection
Staff patrols
Christmas Lights
36. | Christmas Lights | Management and Maintenance | Insurance | Christmas lights securely stored in portakabin at Cemetery.
Staff and Volunteer Training
Health and Safety inspection
|  |  | Regular view of Risk Assessment and planning meetings | Recruiting of event volunteers
Vehicles and Machinery
37. | General Purpose Van | Management and Maintenance | Insurance | New equipment purchased in 2023 (battery rather than petrol).
| John Derre Mini Tractor | Theft and Vandalism | Servicing and testing
| John Derre Pedestrian Mower |  | Repair and Renewal Fund
4
Civic Items
38. | Mayor's Robe Chain and Badge | Theft and damage | Insurance | -
| Coat of Arms and Silver Casket |  | Items stored securely
Display Case, Chest and Contents
Contracts
39. | Contracts | Management | Risk Register | -
|  | Liquidation/Bankruptcy | Contingency Planning
Engagement of specialists
Council Standing Orders
Financial Regulations
Minimise no. of contracts entered into